## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and preprocess historical visa application data so that it can be used for analysis and model training. | Must Have | Dataset availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | As a data analyst, I want to perform exploratory data analysis to identify patterns in visa processing times across countries, seasons, and visa types. | Must Have | Cleaned dataset | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | As a data scientist, I want to train regression models that predict visa processing time based on application features. | Must Have | Feature engineered dataset | Backend Team | Completed
Sprint 3 | Sprint 3 | US004 | As a data scientist, I want to evaluate multiple ML models using metrics like MAE, RMSE, and R² so that the best-performing model can be selected. | Should Have | Trained models | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As an ML engineer, I want to perform hyperparameter tuning on the selected models to optimize their prediction performance. | Should Have | Evaluated models | Backend Team | Completed
Sprint 4 | Sprint 4 | US006 | As an ML engineer, I want to integrate the optimized model into a prediction engine that accepts user inputs and returns estimated visa processing time. | Must Have | Tuned ML model | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a frontend developer, I want to create a web interface where users can enter visa details and view estimated processing time and trends. | Must Have | API endpoints ready | Frontend Team | Completed
Sprint 4 | Sprint 4 | US008 | As a DevOps engineer, I want to deploy the visa processing estimator web application on a cloud platform for demonstration and testing. | Could Have | Backend & frontend integration | Both Teams | Completed
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | TS1 | Collect Historical Visa Datasets | 2026-02-08 | 2026-02-11 | Backend1 | Data Collection | Completed | 10 | bar: Day 1 to Day 4
US001 | TS2 | Clean and preprocess the visa dataset | 2026-02-12 | 2026-02-15 | Backend2 | Data Cleaning | Completed | 6 | bar: Day 2 to Day 5
US002 | TS3 | Perform EDA on visa processing times | 2026-02-21 | 2026-02-25 | Backend3 | Data Processing | Completed | 6 | bar: Day 4 to Day 8
US002 | TS4 | Document patterns and seasonal trends | 2026-02-26 | 2026-03-01 | Backend4 | Analysis | Completed | 4 | bar: Day 1 to Day 4
US003 | TS5 | Feature engineering for regression models | 2026-03-06 | 2026-03-08 | Backend5 | Visualization | Completed | 8 | bar: Day 3 to Day 5
US003 | TS6 | Train initial regression models | 2026-03-09 | 2026-03-11 | Backend6 | Model Training | Completed | 8 | bar: Day 5 to Day 7
US004 | TS7 | Evaluate models with MAE | 2026-03-12 | 2026-03-13 | Backend7 | Model Evaluation | Completed | 4 | bar: Day 6 to Day 7
US005 | TS8 | Perform hyperparameter tuning on top models | 2026-03-14 | 2026-03-15 | Backend8 | Hyperparameter Tuning | Completed | 6 | bar: Day 7 to Day 8
US006 | TS9 | Integrate tuned model into prediction engine API | 2026-03-19 | 2026-03-20 | Backend9 | API Development | Completed | 6 | bar: Day 8 to Day 9
US007 | TS10 | Develop web interface for user inputs | 2026-03-21 | 2026-03-23 | Frontend1 | Frontend Development | Completed | 8 | bar: Day 8 to Day 10
US007 | TS11 | Connect frontend with prediction API | 2026-03-24 | 2026-03-25 | Frontend2 | API Integration | Completed | 6 | bar: Day 10 to Day 11
US008 | TS12 | End-to-end testing in test environment | 2026-03-26 | 2026-03-27 | Both Teams | Testing | Completed | 6 | bar: Day 10 to Day 11
US008 | TS13 | Setup cloud infrastructure and deploy | 2026-03-28 | 2026-03-29 | Both Teams | Cloud Deployment | Completed | 4 | bar: Day 10 to Day 11
Note on E2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 9/15/2016 or 15-Sep-2016 Reply: Marked as resolved Reply: dates are automatically taking that format Re-opened
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 1 work
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 2 work
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 3 work
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 4 work
Note on N3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 5 work
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 6 work
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 7 work
Note on Q3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 8 work
Note on R3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 9 work
Note on S3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 10 work
Note on T3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 11 work
Note on U3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 12 work
Note on V3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 13 work
Note on W3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Dataset contained inconsistent date formats and missing values in some columns such as full_time_position_y_n. | Cleaned dataset, standardized column names, handled missing values, and converted date columns into proper datetime format.
Sprint 1 | Day 2 | Presence of invalid processing times due to incorrect date entries. | Removed invalid rows where decision date occurred before case received date and calculated processing_time_days.
Sprint 1 | Day 3 | Outliers in processing time affecting distribution and model reliability. | Applied IQR-based outlier handling and capped extreme values per visa category.
Sprint 1 | Day 4 | Need for meaningful features for machine learning modeling. | Created time-based features such as year, month, quarter, and seasonal categorization.
Sprint 1 | Day 5 | Difficulty identifying meaningful patterns from raw data. | Performed exploratory data analysis and generated visualizations such as distribution plots, boxplots, and correlation heatmap.
Sprint 2 | Day 1 | High dimensional categorical features affecting modeling efficiency. | Applied encoding and created aggregated features such as state-level and monthly processing statistics.
Sprint 2 | Day 2 | Git conflicts during repository synchronization. | Resolved merge conflicts, completed rebase process, and synchronized repository with remote GitHub repository.
Sprint 3 | Day 1 | Need to design a structured machine learning pipeline for prediction. | Implemented preprocessing pipeline and trained baseline Random Forest regression model.
Sprint 3 | Day 2 | Model performance evaluation and documentation required for project completion. | Evaluated model performance using MAE, RMSE and prepared project documentation.
Sprint 3 | Day 3 | Need to organize project structure and ensure reproducibility for future development and evaluation. | Structured the project repository, added requirements file, and prepared code for version control and collaboration using GitHub.
Sprint 4 | Day 1 | Need to convert trained model into an accessible prediction service. | Designed REST API structure and integrated trained model using FastAPI.
Sprint 4 | Day 2 | Handling request input validation and prediction response formatting. | Implemented API endpoints for model prediction and tested responses using sample requests.
Sprint 5 | Day 1 | Need a simple user interface for interacting with the prediction system. | Designed web interface layout and integrated form-based input for visa prediction parameters.
Sprint 5 | Day 2 | Connecting frontend inputs with backend API service. | Integrated frontend interface with API endpoints to display predicted visa processing time.
Sprint 6 | Day 1 | Preparing the project for deployment and ensuring environment compatibility. | Created requirements file and prepared project structure for deployment.
Sprint 6 | Day 2 | Ensuring application runs correctly in production environment. | Deployed the application and verified API functionality and web interface integration.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7